BUSINESS CONTINUITY MANAGEMENT REVIEW GUIDANCE

ISO 22301:2019 + Amd 1:2024

| Document Owner | Approver |
| --- | --- |
| Business Continuity Manager | Top Management |
| Classification: INTERNAL | Next Review: 2027-09-18 |

# 1. Purpose

Provide practical guidance for preparing and conducting management review so leadership can evaluate current continuity capability, resolve strategic constraints and make evidence-based BCMS decisions.

[Note] A useful management review answers: “Can the organization currently deliver its continuity commitments under credible disruption conditions, and what decisions are needed now?”

# 2. Preparation Principles

Use a defined review period and current data cut-off.

Summarize material trends and exceptions; avoid sending raw trackers without interpretation.

Highlight assumptions that have not been validated through exercise, test or real disruption.

Bring unresolved resource, dependency and ownership decisions to the meeting with clear options.

Separate “activity completed” from evidence that capability is effective.

# 3. Recommended Pre-Read Structure

| Section | What Leadership Needs to See |
| --- | --- |
| Executive summary | Material changes, capability concerns, overdue decisions and recommended actions. |
| Prior actions | Status, evidence, blocked items and effectiveness issues. |
| Context / scope | Significant organizational/external changes, interested-party expectations and relevant climate considerations. |
| BIA / risk | Changes to prioritized activities, impact assumptions, dependencies and disruption risks. |
| Strategies / plans | Readiness/capacity versus approved recovery priorities; material gaps. |
| Exercises / disruptions | What was demonstrated, what failed or remains unproven, and repeat issues. |
| Assurance | KPI/evaluation, audit themes, corrective-action effectiveness and systemic issues. |
| Decisions required | Specific policy, scope, resource, investment, strategy, plan or governance decisions. |

# 4. Decision Quality

| Weak Review Output | Better Review Output |
| --- | --- |
| “BIA update in progress.” | Approve the revised BIA methodology and require completion of high-priority business units by a defined date. |
| “Exercise completed.” | Accept demonstrated strengths, approve remediation for failed objectives and require targeted re-test of the critical capability. |
| “Supplier risk noted.” | Assign owner to verify supplier continuity evidence and approve a fallback strategy if required evidence is not obtained. |
| “Plans reviewed.” | Confirm plan currency and approve alternate-access improvement for plans dependent on the primary network. |

# 5. Questions for Leadership

Are current recovery priorities still aligned with products/services and stakeholder needs?

Where are recovery targets dependent on unproven technology, supplier, facility or staffing assumptions?

What continuity capability has been demonstrated since the previous review?

Which material exercise/audit actions remain open or repeatedly recur?

What investments or management decisions are required to close priority gaps?

Do current objectives and indicators help management make decisions or only report activity?

# 6. Illustrative Decision & Evidence Log

| Data Type | Decision ID | Theme | Decision / Requirement | Owner | Due Date | Evidence Expected | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Example Data | EX-BCMS-MRG-001 | BIA | Approve revised method and completion deadline for high-priority functions. | Business Continuity Manager | 2026-10-31 | Updated method + completion evidence | Illustrative Data |
| Example Data | EX-BCMS-MRG-002 | Technology | Require capacity test before accepting current recovery target. | IT Resilience Lead | 2026-11-15 | Test result + decision | Illustrative Data |
| Example Data | EX-BCMS-MRG-003 | Supplier | Verify continuity evidence for critical single-source supplier and define fallback. | Supply Chain Director | 2026-12-15 | Supplier evidence + fallback approval | Illustrative Data |
| Example Data | EX-BCMS-MRG-004 | Exercise | Re-test failed cross-functional recovery objective after remediation. | Exercise Coordinator | 2027-02-15 | Re-test report | Illustrative Data |
| Example Data | EX-BCMS-MRG-005 | Document Access | Verify selected critical plans remain accessible during primary repository outage. | BCMS Documentation Owner | 2026-09-30 | Access test evidence | Illustrative Data |
| Actual Data |  |  |  |  |  |  |  |
| Actual Data |  |  |  |  |  |  |  |
| Actual Data |  |  |  |  |  |  |  |

[Note] The example decision log is for training only. Controlled management-review records must contain the decisions actually approved by management.

# 7. Common Failure Modes

Meeting focuses on document completion instead of continuity capability.

No clear link from exercise/audit findings to resource or strategy decisions.

Actions are assigned without due date or closure evidence.

Leadership receives only averages that hide critical high-impact services or dependencies.

Previous actions are reported “closed” without checking whether the underlying weakness was resolved.

# References

ISO 22301:2019 — Security and resilience — Business continuity management systems — Requirements.

ISO 22301:2019/Amd 1:2024 — Climate action changes.

ISO 22313:2020 — Security and resilience — Business continuity management systems — Guidance on the use of ISO 22301.

Controlled organization-specific BCMS policies, BIA records, risk assessments, continuity strategies, plans, exercise records, audit records and improvement actions.

# Revision and Approval

| Version | Date | Change | Document Owner | Approver |
| --- | --- | --- | --- | --- |
| 1.0 | 2026-09-18 | Initial issue | Business Continuity Manager | Top Management |