COMPLIANCE IMPLEMENTATION PROJECT PLAN

ISO 37301:2021 + Amd 1:2024

ISO 37301 Compliance Management System Implementation Plan

| Document Owner | Approver |
| --- | --- |
| CMS Implementation Lead / Chief Compliance Officer | Project Sponsor / Top Management |
| Classification: INTERNAL | Next Review: 2027-09-18 |

[Note] This is a practical implementation baseline. Replace bracketed organization fields, dates, jurisdiction-specific obligations and project assumptions before controlled release.

# 1. Project Purpose and Objectives

Establish, implement and transition an effective Compliance Management System aligned with ISO 37301:2021 and its 2024 climate-action amendment, integrated with existing governance and business processes.

| Project objective | Success evidence |
| --- | --- |
| Establish CMS governance and scope | Approved sponsor, governance, roles, scope and implementation roadmap. |
| Identify obligations and compliance risks | Controlled obligation sources, applicability ownership and risk assessment. |
| Design proportionate controls and reporting | Policies, controls, due diligence, speak-up, investigation and monitoring arrangements operating. |
| Build competence and culture | Role-based competence, communications and evidence of awareness. |
| Demonstrate assurance and improvement | Compliance evaluation, internal audit, corrective action and management review completed. |
| Prepare for certification/readiness decision if desired | Evidence pack, closed critical gaps and management readiness decision. |

# 2. Scope and Assumptions

Project scope: [ORGANIZATION / ENTITIES / SITES / FUNCTIONS / GEOGRAPHIES]. Interfaces with existing risk, legal, HR, internal audit, procurement, information security, finance and investigation processes should be identified early. Certification is optional unless separately approved as a project objective.

# 3. Project Governance

| Role | Core responsibility |
| --- | --- |
| Project Sponsor / Top Management | Set direction, remove barriers, approve resources and make readiness decisions. |
| Chief Compliance Officer / CMS Owner | Own CMS design, technical integrity and operational transition. |
| Project Manager | Plan schedule, dependencies, actions, reporting and delivery controls. |
| Workstream Leads | Deliver assigned governance, risk, controls, people, third-party, assurance and documentation outputs. |
| Legal / Subject-Matter Experts | Verify jurisdiction-specific obligations and specialist requirements. |
| Internal Audit / Assurance | Maintain appropriate independence while advising on readiness and later auditing the CMS. |

# 4. Implementation Roadmap

| Phase | Workstream | Indicative timing | Key deliverables |
| --- | --- | --- | --- |
| Phase 1 | Mobilize & Baseline | Weeks 1–4 | Sponsor, scope, governance, project plan, initial document map, initial gap assessment. |
| Phase 2 | Context, Obligations & Risk | Weeks 3–8 | Context/interested parties, obligation methodology/register, compliance risk assessment. |
| Phase 3 | CMS Design | Weeks 6–14 | Policy, roles, objectives, controls, speak-up/investigation, third-party/supplier and documented-information framework. |
| Phase 4 | Implement & Embed | Weeks 10–22 | Control rollout, communications, training, system/repository setup, operational records. |
| Phase 5 | Evaluate & Improve | Weeks 18–28 | Monitoring, compliance evaluation, internal audit, corrective action and management review. |
| Phase 6 | Readiness & Handover | Weeks 26–32 | Evidence consolidation, residual-gap closure, readiness decision, operational handover / certification preparation if applicable. |

# 5. Key Workstreams and Deliverables

| Workstream | Core deliverables |
| --- | --- |
| Governance & Context | Scope, governance charter, roles, context and interested-party assessment. |
| Compliance Obligations | Source methodology, obligations register, applicability and change-monitoring ownership. |
| Compliance Risk | Risk methodology, risk register, priorities and treatment/control mapping. |
| Policy, Controls & Operations | Policy, procedures, approvals, key controls and evidence requirements. |
| Speak-Up & Investigations | Channel, triage, investigation, confidentiality, escalation and remediation process. |
| Third Parties & Suppliers | Risk classification, due diligence, contracts, monitoring and evaluation. |
| People, Culture & Competence | Training needs, role-based learning, awareness, leadership communication and culture indicators. |
| Documented Information | Document map, templates, repository, control and retention arrangements. |
| Monitoring, Evaluation & Audit | CMS indicators, compliance evaluation, audit programme and corrective action. |
| Management Review & Handover | Management review, improvement decisions, residual-gap closure and business-as-usual ownership. |

# 6. Illustrative Implementation Task Tracker

| Data Type | Task ID | Task / Deliverable | Owner | Target Date | Priority | Status | Dependency / Note |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Example Data | EX-CMS-P01 | Confirm CMS sponsor, governance and implementation scope. | Project Sponsor | 2026-09-30 | High | Completed | Illustrative Data |
| Example Data | EX-CMS-P02 | Validate methodology and ownership for authoritative compliance-obligation sources. | Compliance Manager | 2026-10-15 | High | In Progress | Requires legal/SME input |
| Example Data | EX-CMS-P03 | Complete initial enterprise compliance risk assessment. | Compliance Risk Lead | 2026-11-15 | High | In Progress | Depends on scope and obligations baseline |
| Example Data | EX-CMS-P04 | Design higher-risk third-party due diligence and refresh controls. | Third-Party Risk Manager | 2026-12-15 | Medium | Not Started | Depends on risk criteria |
| Example Data | EX-CMS-P05 | Plan first internal CMS audit and management review. | Compliance Assurance Lead | 2027-02-15 | Medium | Open | Requires sufficient operating evidence |

[Note] The five tracker rows are Illustrative Data only. Keep project reporting separate from business-as-usual compliance incidents or legal conclusions.

# 7. Project Risks and Dependencies

| Project risk / dependency | Mitigation / control |
| --- | --- |
| Unclear jurisdictional obligation ownership | Assign legal/compliance SMEs and authoritative-source owners early. |
| Project becomes documentation-only | Define operating evidence and effectiveness criteria for each major control. |
| Insufficient management time / decisions | Use scheduled steering governance and explicit decision log. |
| Existing systems/processes are not integrated | Map interfaces to HR, risk, procurement, finance, audit, case management and IT. |
| Training delivered before processes are stable | Sequence training after core roles and procedures are approved; refresh as controls change. |
| Assurance performed before enough evidence exists | Use readiness checks and staged sampling; schedule audit after meaningful operating period. |

# 8. Reporting and Change Control

Report progress at the agreed cadence using milestone status, overdue actions, key risks, decisions required and evidence-readiness. Changes to scope, timing, resources or critical deliverables should be approved by the designated project authority and recorded in the decision/change log.

# 9. Readiness Gates

| Gate | Minimum evidence before approval |
| --- | --- |
| G1 — Mobilization complete | Sponsor, governance, scope, project plan and initial assessment approved. |
| G2 — Design approved | Core CMS framework, risk method, obligation process, policy and key controls approved. |
| G3 — Operational evidence available | Key controls operating with records, competence and communication evidence. |
| G4 — Assurance complete | Compliance evaluation, internal audit and corrective actions sufficiently progressed. |
| G5 — Management readiness / handover | Management review completed; critical residual gaps have approved disposition; BAU ownership accepted. |

# References and Related Sources

| Reference | Use in this document | Source / Location |
| --- | --- | --- |
| ISO 37301:2021 | Compliance management systems — requirements with guidance for use | https://www.iso.org/standard/75080.html |
| ISO 37301:2021/Amd 1:2024 | Climate action changes | https://www.iso.org/standard/88422.html |
| Organization CMS documented information | Applicable policies, registers, procedures, audit records and management-review records | [INTERNAL SOURCE / REPOSITORY] |

# Revision and Approval

| Version | Date | Change | Document Owner | Approver |
| --- | --- | --- | --- | --- |
| 1.0 | 2026-09-18 | Initial issue | CMS Implementation Lead / Chief Compliance Officer | Project Sponsor / Top Management |