## Instructions
Environmental Management Implementation Project Plan
Document Code: EMS-PLN-001 ¦ Version: 1.0 ¦ Effective Date: 2026-09-18 ¦ Applied Standard: ISO 14001:2026 ¦ Classification: INTERNAL
Copyright © ISO Toolkits ¦ www.iso-toolkits.org ¦ info@iso-toolkits.org
Purpose
Use this workbook to plan and control EMS implementation from project initiation through environmental aspects, compliance obligations, operational controls, audit, management review and certification readiness.
1 | The first five task rows contain varied Example Data and are excluded from Dashboard/KPI.
2 | Set Data Type = Actual Data for each task when the organization adopts and manages it.
3 | Set realistic dates based on sites, activities, environmental aspects, obligations and resources.
4 | Assign one accountable owner; supporting contributors may be noted separately.
5 | Sequence aspect/compliance analysis before detailed operational controls and objective setting.
6 | Evidence should show operating controls, not only document completion.
7 | Use Dashboard to identify actual overdue, blocked and high-priority work.
8 | ISO baseline source: https://www.iso.org/standard/14001

## Project Plan
EMS Implementation Project Plan - Main Tracker
Document Code: EMS-PLN-001 ¦ Version: 1.0 ¦ Effective Date: 2026-09-18 ¦ Applied Standard: ISO 14001:2026 ¦ Classification: INTERNAL
Copyright © ISO Toolkits ¦ www.iso-toolkits.org ¦ info@iso-toolkits.org
The first 5 populated rows contain Example Data / Illustrative Data. They are excluded from Dashboard/KPI calculations. Replace or delete them before operational use.
Data Type | Task ID | Phase | Task | Practical Deliverable | Owner | Priority | Start Date | Due Date | Status | % Complete | Dependency | Schedule Flag | Evidence / Link | Notes
Example Data | EX-P1-01 | 1. Initiation | Appoint EMS sponsor and implementation lead | Named sponsor and implementation lead | Managing Director | High | 2026-08-03 | 2026-08-07 | Completed | 100% |  |  | Signed appointment memo | Illustrative initiation task
Example Data | EX-P2-01 | 2. Context & Scope | Analyze internal and external environmental context | Context analysis including relevant environmental conditions | EMS Manager | High | 2026-08-10 | 2026-08-28 | Completed | 100% | EX-P1-01 |  | Context workshop record | Illustrative completed analysis
Example Data | EX-P4-03 | 4. Planning | Identify environmental aspects and impacts using life-cycle perspective | Aspects & impacts register | Environmental Coordinator | High | 2026-09-01 | 2026-09-25 | In Progress | 65% | EX-P2-01 |  | Aspect workshop notes | Illustrative ongoing planning
Example Data | EX-P6-02 | 6. Support | Deliver EMS awareness and role-specific training | Training / awareness evidence | HR & Training Manager | Medium | 2026-09-15 | 2026-10-10 | Not Started | 0% | Competence needs |  | Training plan draft | Illustrative future task
Example Data | EX-P7-06 | 7. Operations | Conduct environmental emergency drills or tests | Drill/test records and actions | Site Manager | Low | 2026-10-01 | 2026-11-15 | Blocked | 20% | Emergency plan |  | Awaiting external responder schedule | Illustrative blocked task
| P1-01 | 1. Initiation | Appoint EMS sponsor and implementation lead | Named sponsor and implementation lead
| P1-02 | 1. Initiation | Define EMS implementation objectives and governance | Approved implementation brief / charter
| P1-03 | 1. Initiation | Identify implementation team and key process/site representatives | Implementation team and governance structure
| P1-04 | 1. Initiation | Confirm ISO 14001:2026 baseline and certification intent | Baseline and project assumptions
| P2-01 | 2. Context & Scope | Analyze internal and external environmental context | Context analysis including relevant environmental conditions
| P2-02 | 2. Context & Scope | Identify interested parties and relevant environmental needs/expectations | Interested parties register
| P2-03 | 2. Context & Scope | Define EMS scope, sites, activities and interfaces | Approved EMS scope
| P2-04 | 2. Context & Scope | Map EMS processes and operational interfaces | EMS process map
| P3-01 | 3. Gap Analysis | Perform EMS gap analysis | Completed gap assessment with evidence
| P3-02 | 3. Gap Analysis | Prioritize gaps and approve action plan | Gap analysis action plan
| P4-01 | 4. Planning | Define environmental aspect identification and significance method | Approved aspect / impact method
| P4-02 | 4. Planning | Identify activities, products and services for aspect review | Aspect review inventory
| P4-03 | 4. Planning | Identify environmental aspects and impacts using life-cycle perspective | Aspects & impacts register
| P4-04 | 4. Planning | Evaluate significant environmental aspects | Significance results and rationale
| P4-05 | 4. Planning | Identify EMS risks and opportunities | Risks/opportunities register
| P4-06 | 4. Planning | Identify compliance obligations from authoritative sources | Compliance obligations register
| P4-07 | 4. Planning | Establish environmental objectives, indicators and plans | Objectives / KPI register
| P4-08 | 4. Planning | Define planning-of-change controls for EMS-relevant changes | Change-control method
| P5-01 | 5. Leadership | Approve environmental policy | Approved and communicated policy
| P5-02 | 5. Leadership | Assign environmental roles, responsibilities and authorities | Roles/responsibilities matrix
| P5-03 | 5. Leadership | Integrate EMS responsibilities into business/operational governance | Governance evidence
| P6-01 | 6. Support | Define competence needs for environmental responsibilities | Competence matrix / plan
| P6-02 | 6. Support | Deliver EMS awareness and role-specific training | Training / awareness evidence
| P6-03 | 6. Support | Establish internal/external environmental communication arrangements | Communication plan / method
| P6-04 | 6. Support | Establish documented information controls | Controlled EMS information
| P7-01 | 7. Operations | Define operational criteria for significant aspects and obligations | Operational control matrix
| P7-02 | 7. Operations | Implement controls for waste, emissions, discharges, energy/resource use or other relevant aspects | Operational evidence
| P7-03 | 7. Operations | Integrate life-cycle considerations into design/procurement/supplier controls where relevant | Procurement / supplier controls
| P7-04 | 7. Operations | Implement environmental management of change | Change review records
| P7-05 | 7. Operations | Establish environmental emergency preparedness and response | Emergency plans / controls
| P7-06 | 7. Operations | Conduct environmental emergency drills or tests | Drill/test records and actions
| P8-01 | 8. Performance | Establish monitoring and measurement programme | Monitoring / measurement plan
| P8-02 | 8. Performance | Establish evaluation of compliance obligations | Compliance evaluation process and schedule
| P8-03 | 8. Performance | Monitor objective/KPI trends and significant-aspect performance | Performance dashboard / reviews
| P8-04 | 8. Performance | Evaluate environmental performance and identify adverse trends | Evaluation records / actions
| P9-01 | 9. Assurance | Plan and conduct internal EMS audit | Audit report and findings
| P9-02 | 9. Assurance | Close audit findings and verify corrective-action effectiveness | Verified closure evidence
| P9-03 | 9. Assurance | Conduct EMS management review | Management review minutes and decisions
| P10-01 | 10. Improvement | Implement incident/nonconformity and corrective-action process | Corrective-action records
| P10-02 | 10. Improvement | Demonstrate continual improvement in EMS and environmental performance | Improvement evidence
| P11-01 | 11. Readiness | Complete certification readiness review | Readiness assessment
| P11-02 | 11. Readiness | Close material readiness gaps | Critical actions closed
| P11-03 | 11. Readiness | Prepare evidence index and audit logistics | Audit evidence index / logistics
Formulas:
Schedule Flag = IF([Data Type]<>"Actual Data","",IF(OR([Status]="Completed",[Status]="Closed"),"Closed",IF([Due Date]="","",IF([Due Date]<TODAY(),"Overdue",IF([Due Date]-TODAY()<=7,"Due Soon","On Track")))))

## Dashboard
EMS Implementation Project Dashboard
Document Code: EMS-PLN-001 ¦ Version: 1.0 ¦ Effective Date: 2026-09-18 ¦ Applied Standard: ISO 14001:2026 ¦ Classification: INTERNAL
Copyright © ISO Toolkits ¦ www.iso-toolkits.org ¦ info@iso-toolkits.org
KPI | Result | Actual Status | Count
Template Tasks | 43 | Not Started | 0
Actual Tasks Activated | 0 | In Progress | 0
Completed | 0 | Blocked | 0
In Progress | 0 | Completed | 0
Blocked | 0 | Closed | 0
Not Started | 0
Overdue | 0
High Priority Open | 0
Average % Complete | 0%
Example Rows (excluded) | 5

## Reference Data
Reference Data
Document Code: EMS-PLN-001 ¦ Version: 1.0 ¦ Effective Date: 2026-09-18 ¦ Applied Standard: ISO 14001:2026 ¦ Classification: INTERNAL
Copyright © ISO Toolkits ¦ www.iso-toolkits.org ¦ info@iso-toolkits.org
List | Value | Description | Source / Note
Data Type | Example Data | Illustrative row; excluded from operational Dashboard/KPI.
Data Type | Actual Data | Operational row; included in Dashboard/KPI.
Priority | High
Priority | Medium
Priority | Low
Status | Not Started
Status | In Progress
Status | Blocked
Status | Completed
Status | Closed
Standard | ISO 14001:2026 | Current EMS baseline used for this toolkit. | https://www.iso.org/standard/14001

## Revision History
Revision History
Document Code: EMS-PLN-001 ¦ Version: 1.0 ¦ Effective Date: 2026-09-18 ¦ Applied Standard: ISO 14001:2026 ¦ Classification: INTERNAL
Copyright © ISO Toolkits ¦ www.iso-toolkits.org ¦ info@iso-toolkits.org
Version | Date | Description
1.0 | 2026-09-18 | Initial issue