## Instructions
Service Management Implementation Project Plan
Document Code: CCC-PLN-002 ¦ Version: 1.0 ¦ Effective Date: 2026-09-18 ¦ Applied Standard: ISO 18295-1:2017 / ISO 18295-2:2017 ¦ Classification: INTERNAL
Copyright © ISO Toolkits ¦ www.iso-toolkits.org ¦ info@iso-toolkits.org
[Note] Project durations, resource levels and milestones are illustrative. Tailor the plan to the organization's size, service complexity, client model and current maturity.
Use this workbook to plan and control implementation or enhancement of a customer contact-centre service management system aligned with ISO 18295. The plan covers initiation, current-state assessment, service-system design, implementation, validation and handover/continual improvement.
1 | The first five project rows are Illustrative Data and are excluded from Actual KPI/Summary.
2 | The remaining template tasks provide a practical implementation work breakdown; set Data Type = Actual Data as the project is baselined.
3 | Replace role placeholders with named accountable owners and approved dates.
4 | Use dependencies to coordinate client, workforce, quality, knowledge, technology, complaint and continuity workstreams.
5 | Track completion based on evidence/deliverables, not elapsed time alone.
6 | Escalate blocked high-priority tasks through the project governance process.
7 | Review changes to scope, service requirements and KPI definitions through controlled project/change governance.
8 | Dashboard KPI uses Actual Data only; charts show Illustrative Data until Actual Data is entered.
9 | Use the project plan together with the Gap Analysis and Action Plan to avoid duplicate implementation actions.
10 | Official ISO sources: https://www.iso.org/standard/64739.html ¦ https://www.iso.org/standard/64740.html

## Project Plan
Service Management Implementation Project Plan - Main Tracker
Document Code: CCC-PLN-002 ¦ Version: 1.0 ¦ Effective Date: 2026-09-18 ¦ Applied Standard: ISO 18295-1:2017 / ISO 18295-2:2017 ¦ Classification: INTERNAL
Copyright © ISO Toolkits ¦ www.iso-toolkits.org ¦ info@iso-toolkits.org
[Note] The first 5 rows are Illustrative Data. The remaining task rows are a practical work-breakdown template; assign Actual Data, names and approved dates when the project is baselined.
Data Type | Task ID | Phase | Workstream | Task / Activity | Deliverable / Evidence | Owner Role | Priority | Predecessor(s) | Planned Start | Planned Finish | % Complete | Status | Schedule Flag | Actual Finish | Decision / Dependency | Reviewer | Notes
Example Data | EX-SMP-001 | 1 - Initiate | Project Governance | Confirm executive sponsor and implementation governance. | Approved governance charter | Executive Sponsor | High |  | 2026-08-03 | 2026-08-07 | 100% | Completed |  |  |  | Project Manager | Illustrative Data
Example Data | EX-SMP-006 | 2 - Assess | Gap Analysis | Complete ISO 18295 service management gap analysis. | Gap analysis report | Lead Assessor | High | EX-SMP-001 | 2026-08-10 | 2026-08-28 | 100% | Completed |  |  |  | Project Manager | Illustrative Data
Example Data | EX-SMP-020 | 3 - Design | Quality Framework | Define QA criteria, sampling, calibration and action follow-up. | Approved QA framework | Quality Manager | High | EX-SMP-006 | 2026-09-01 | 2026-09-30 | 70% | In Progress |  |  | Calibration threshold approval pending | Project Manager | Illustrative Data
Example Data | EX-SMP-027 | 4 - Implement | Training | Deliver role-based training and management/agent awareness. | Training completion evidence | Training Lead | Medium | EX-SMP-020 | 2026-10-01 | 2026-10-31 | 20% | Blocked |  |  | Final training content awaits approved procedures | Project Manager | Illustrative Data
Example Data | EX-SMP-033 | 5 - Validate | Internal Audit | Conduct internal service management audit. | Audit report / findings | Lead Auditor | Low | EX-SMP-027 | 2026-11-16 | 2026-11-27 | 0% | Not Started |  |  | Dependent on operating evidence from implementation | Project Manager | Illustrative Data
| SMP-001 | 1 - Initiate | Project Governance | Confirm executive sponsor and implementation governance. | Approved project governance / steering structure | Executive Sponsor | High |  |  |  | 0%
| SMP-002 | 1 - Initiate | Project Governance | Confirm service-management implementation objectives, success criteria and business outcomes. | Project charter / objectives | Project Manager | High | SMP-001 |  |  | 0%
| SMP-003 | 1 - Initiate | Scope | Define organizational, service, channel, site and client scope. | Approved implementation scope | Service Director | High | SMP-001 |  |  | 0%
| SMP-004 | 1 - Initiate | Stakeholders | Identify key internal/external stakeholders and implementation interfaces. | Stakeholder map | Project Manager | Medium | SMP-003 |  |  | 0%
| SMP-005 | 1 - Initiate | Plan | Baseline detailed project schedule, resources, communications and risks. | Approved project plan | Project Manager | High | SMP-001,SMP-003 |  |  | 0%
| SMP-006 | 2 - Assess | Gap Analysis | Complete ISO 18295 service management gap analysis. | Gap analysis | Lead Assessor | High | SMP-003 |  |  | 0%
| SMP-007 | 2 - Assess | Process Review | Map current customer-contact journeys, channels and handoffs. | Current-state process map | Service Excellence Lead | Medium | SMP-003 |  |  | 0%
| SMP-008 | 2 - Assess | KPI Review | Review KPI definitions, source systems, targets and reporting integrity. | KPI assessment | Performance Manager | High | SMP-006 |  |  | 0%
| SMP-009 | 2 - Assess | Quality Review | Assess QA framework, sampling, evaluator competence and calibration. | QA assessment | Quality Manager | High | SMP-006 |  |  | 0%
| SMP-010 | 2 - Assess | Workforce Review | Assess forecasting, scheduling, competence, training and coaching controls. | Workforce assessment | Workforce Manager | Medium | SMP-006 |  |  | 0%
| SMP-011 | 2 - Assess | Knowledge Review | Assess knowledge governance, content lifecycle and agent access. | Knowledge assessment | Knowledge Manager | Medium | SMP-006 |  |  | 0%
| SMP-012 | 2 - Assess | Complaints / Feedback | Assess complaint, feedback and service-recovery processes. | CX assessment | Customer Experience Manager | High | SMP-006 |  |  | 0%
| SMP-013 | 2 - Assess | Technology / Continuity | Assess platform availability, incident handling and service continuity. | Technology/continuity assessment | Technology Manager | High | SMP-006 |  |  | 0%
| SMP-014 | 2 - Assess | Client / Outsourcing | Assess client governance, SLA interfaces and outsourced provider controls where applicable. | Client/provider assessment | Client Governance Lead | Medium | SMP-006 |  |  | 0%
| SMP-015 | 2 - Assess | Action Planning | Prioritize implementation gaps and approve action plan. | Approved gap action plan | Project Steering Group | High | SMP-006 |  |  | 0%
| SMP-016 | 3 - Design | Service Framework | Design service management process framework and governance. | Service management framework | Service Director | High | SMP-015 |  |  | 0%
| SMP-017 | 3 - Design | Policy / Objectives | Develop service policy, objectives and indicators guidance. | Policy/objectives package | Service Director | Medium | SMP-016 |  |  | 0%
| SMP-018 | 3 - Design | Documented Information | Define document/record control requirements and repository structure. | Documented information design | Document Controller | Medium | SMP-016 |  |  | 0%
| SMP-019 | 3 - Design | Interaction Standards | Define customer interaction handling, escalation and record requirements. | Interaction standard / procedure | Operations Manager | High | SMP-016 |  |  | 0%
| SMP-020 | 3 - Design | Quality Framework | Define QA criteria, sampling, calibration and action follow-up. | QA framework | Quality Manager | High | SMP-009,SMP-016 |  |  | 0%
| SMP-021 | 3 - Design | KPI Framework | Approve KPI dictionary, targets, reporting cadence and owners. | KPI register / dashboard design | Performance Manager | High | SMP-008,SMP-016 |  |  | 0%
| SMP-022 | 3 - Design | Complaints | Design complaint handling, escalation, learning and reporting controls. | Complaint process | Customer Experience Manager | High | SMP-012,SMP-016 |  |  | 0%
| SMP-023 | 3 - Design | Workforce / Competence | Define competence, training, coaching and supervisory requirements. | Competence/training framework | Workforce Manager | Medium | SMP-010,SMP-016 |  |  | 0%
| SMP-024 | 3 - Design | Knowledge | Define knowledge lifecycle, approval, versioning and change controls. | Knowledge governance | Knowledge Manager | Medium | SMP-011,SMP-016 |  |  | 0%
| SMP-025 | 3 - Design | Technology / Continuity | Define system availability, incident, fallback and service continuity requirements. | Technology/continuity controls | Technology Manager | High | SMP-013,SMP-016 |  |  | 0%
| SMP-026 | 4 - Implement | Document Deployment | Issue controlled procedures, guidance, checklists and registers. | Controlled document set | Document Controller | High | SMP-017,SMP-018,SMP-019 |  |  | 0%
| SMP-027 | 4 - Implement | Training | Deliver role-based training and management/agent awareness. | Training completion evidence | Training Lead | High | SMP-026 |  |  | 0%
| SMP-028 | 4 - Implement | KPI / Dashboard | Configure KPI capture, reconciliation and management dashboards. | Operational dashboard | Performance Manager | High | SMP-021 |  |  | 0%
| SMP-029 | 4 - Implement | Quality / Calibration | Implement QA sampling and calibration cycle. | QA operating evidence | Quality Manager | High | SMP-020,SMP-027 |  |  | 0%
| SMP-030 | 4 - Implement | Complaint Process | Deploy complaint workflow, escalation and trend reporting. | Complaint handling evidence | Customer Experience Manager | High | SMP-022,SMP-027 |  |  | 0%
| SMP-031 | 4 - Implement | Knowledge | Publish approved knowledge content and change controls. | Knowledge-base evidence | Knowledge Manager | Medium | SMP-024,SMP-027 |  |  | 0%
| SMP-032 | 4 - Implement | Continuity | Test critical service fallback and communication arrangements. | Continuity test evidence | Technology Manager | High | SMP-025 |  |  | 0%
| SMP-033 | 5 - Validate | Internal Audit | Conduct internal service management audit. | Audit report / findings | Lead Auditor | High | SMP-026,SMP-029,SMP-030,SMP-032 |  |  | 0%
| SMP-034 | 5 - Validate | Customer Contact Evaluation | Run calibrated sample of customer-contact evaluations. | Evaluation results | Quality Manager | Medium | SMP-029 |  |  | 0%
| SMP-035 | 5 - Validate | Performance Review | Review initial KPI, quality, complaint and customer satisfaction trends. | Validation performance report | Service Director | High | SMP-028,SMP-029,SMP-030,SMP-034 |  |  | 0%
| SMP-036 | 5 - Validate | Corrective Action | Close high-priority audit/validation gaps with effectiveness evidence. | Corrective action evidence | Project Manager | High | SMP-033,SMP-035 |  |  | 0%
| SMP-037 | 5 - Validate | Management Review | Conduct implementation management review and approve readiness. | Management review minutes | Executive Sponsor | High | SMP-036 |  |  | 0%
| SMP-038 | 6 - Handover & Improve | Handover | Transfer ownership of documents, dashboards, actions and governance calendar. | Operational handover pack | Project Manager | High | SMP-037 |  |  | 0%
| SMP-039 | 6 - Handover & Improve | Improvement Plan | Establish post-implementation improvement backlog and review cadence. | Improvement plan | Service Director | Medium | SMP-037 |  |  | 0%
| SMP-040 | 6 - Handover & Improve | Project Closure | Complete lessons learned, closure report and sponsor sign-off. | Project closure report | Project Manager | Medium | SMP-038,SMP-039 |  |  | 0%
Formulas:
Schedule Flag = IF([Data Type]<>"Actual Data","",IF(OR([Status]="Completed",[Status]="N/A"),[Status],IF([Planned Finish]="","",IF([Planned Finish]<TODAY(),"Overdue",IF([Planned Finish]-TODAY()<=7,"Due Soon","On Track")))))

## Dashboard
Service Management Implementation Dashboard
Document Code: CCC-PLN-002 ¦ Version: 1.0 ¦ Effective Date: 2026-09-18 ¦ Applied Standard: ISO 18295-1:2017 / ISO 18295-2:2017 ¦ Classification: INTERNAL
Copyright © ISO Toolkits ¦ www.iso-toolkits.org ¦ info@iso-toolkits.org
[Note] Example Data is used only to demonstrate charts while no Actual Data exists. KPI/Summary always excludes Example Data.
Chart Data Mode | Illustrative Data
Actual KPI | Result
Actual Tasks | 0
Completed | 0
In Progress | 0
Blocked | 0
Not Started | 0
Overdue | 0
High Priority Open | 0
Average % Complete | 0%
Actual Completion % | 0%
Example Rows (excluded) | 5

## Chart Data
Chart Data - Project Plan
Document Code: CCC-PLN-002 ¦ Version: 1.0 ¦ Effective Date: 2026-09-18 ¦ Applied Standard: ISO 18295-1:2017 / ISO 18295-2:2017 ¦ Classification: INTERNAL
Copyright © ISO Toolkits ¦ www.iso-toolkits.org ¦ info@iso-toolkits.org
Chart Data Mode | Value
Mode | Illustrative Data
Status | Count | Phase | Count
Not Started | 1 | 1 - Initiate | 1
In Progress | 1 | 2 - Assess | 1
Blocked | 1 | 3 - Design | 1
Completed | 2 | 4 - Implement | 1
N/A | 0 | 5 - Validate | 1
|  | 6 - Handover & Improve | 0

## Reference Data
Reference Data
Document Code: CCC-PLN-002 ¦ Version: 1.0 ¦ Effective Date: 2026-09-18 ¦ Applied Standard: ISO 18295-1:2017 / ISO 18295-2:2017 ¦ Classification: INTERNAL
Copyright © ISO Toolkits ¦ www.iso-toolkits.org ¦ info@iso-toolkits.org
List | Value | Description | Source / Note
Data Type | Example Data | Illustrative row; excluded from Actual KPI/Summary.
Data Type | Actual Data | Operational row; included in Actual KPI/Summary.
Priority | High
Priority | Medium
Priority | Low
Standard | ISO 18295-1:2017 | Requirements for customer contact centres. | https://www.iso.org/standard/64739.html
Standard | ISO 18295-2:2017 | Requirements for clients using services of customer contact centres. | https://www.iso.org/standard/64740.html
Phase | 1 - Initiate
Phase | 2 - Assess
Phase | 3 - Design
Phase | 4 - Implement
Phase | 5 - Validate
Phase | 6 - Handover & Improve
Status | Not Started
Status | In Progress
Status | Blocked
Status | Completed
Status | N/A
[Note] Jurisdiction-specific privacy, recording, consumer-protection, accessibility, employment or sector requirements must be verified from authoritative sources before controlled use.

## Revision History
Revision History
Document Code: CCC-PLN-002 ¦ Version: 1.0 ¦ Effective Date: 2026-09-18 ¦ Applied Standard: ISO 18295-1:2017 / ISO 18295-2:2017 ¦ Classification: INTERNAL
Copyright © ISO Toolkits ¦ www.iso-toolkits.org ¦ info@iso-toolkits.org
Version | Date | Description
1.0 | 2026-09-18 | Initial issue