## Instructions
Privacy Implementation Project Plan
Document Code: PIMS-PLN-001 ¦ Version: 1.0 ¦ Effective Date: 2026-09-18 ¦ Applied Standard: ISO/IEC 27701:2025 ¦ Classification: INTERNAL
Copyright © ISO Toolkits ¦ www.iso-toolkits.org ¦ info@iso-toolkits.org
[Note] Project timing, legal workstreams, resources and certification objectives must be tailored to the organization. This plan does not determine applicable privacy law or replace legal advice.
Use this workbook to plan implementation or major enhancement of a Privacy Information Management System (PIMS) aligned with ISO/IEC 27701:2025. The plan covers project initiation, current-state assessment, PIMS design, operational implementation, validation and handover/continual improvement.
1 | The first five project rows are Illustrative Data and are excluded from Actual KPI/Summary.
2 | The remaining rows provide a practical implementation work breakdown; set Data Type = Actual Data when the plan is baselined.
3 | Replace role placeholders with named accountable owners and approved dates.
4 | Coordinate privacy, information security, legal/compliance, data governance, procurement, HR, technology and operational workstreams.
5 | Track completion against tangible evidence/deliverables, not elapsed time alone.
6 | Use verified applicable privacy obligations as a separate input to the PIMS requirements framework.
7 | Avoid placing unnecessary real PII in project evidence; reference controlled repositories where appropriate.
8 | Dashboard KPI uses Actual Data only; charts use Illustrative Data until Actual Data exists.
9 | Use the Gap Analysis and Action Plan to control detailed remediation without duplicating project tasks unnecessarily.
10 | Official ISO source: https://www.iso.org/standard/27701

## Project Plan
Privacy Implementation Project Plan - Main Tracker
Document Code: PIMS-PLN-001 ¦ Version: 1.0 ¦ Effective Date: 2026-09-18 ¦ Applied Standard: ISO/IEC 27701:2025 ¦ Classification: INTERNAL
Copyright © ISO Toolkits ¦ www.iso-toolkits.org ¦ info@iso-toolkits.org
[Note] The first 5 rows are Illustrative Data. The remaining tasks are a practical work-breakdown template; assign Actual Data, named owners and approved dates during project baselining.
Data Type | Task ID | Phase | Workstream | Task / Activity | Deliverable / Evidence | Owner Role | Priority | Predecessor(s) | Planned Start | Planned Finish | % Complete | Status | Schedule Flag | Actual Finish | Decision / Dependency | Reviewer | Notes
Example Data | EX-PIP-001 | 1 - Initiate | Governance | Confirm executive sponsor and PIMS implementation governance. | Approved project governance charter | Executive Sponsor | High |  | 2026-08-03 | 2026-08-07 | 100% | Completed |  |  |  | Project Manager | Illustrative Data
Example Data | EX-PIP-006 | 2 - Assess | Gap Analysis | Complete ISO/IEC 27701 privacy gap analysis. | Privacy gap analysis report | Lead Assessor | High | EX-PIP-001 | 2026-08-10 | 2026-08-28 | 100% | Completed |  |  |  | Project Manager | Illustrative Data
Example Data | EX-PIP-020 | 3 - Design | Privacy Risk | Define approved privacy risk and impact assessment method. | Privacy risk / impact method | Privacy Risk Lead | High | EX-PIP-006 | 2026-09-01 | 2026-09-30 | 70% | In Progress |  |  | Risk acceptance criteria awaiting steering approval | Project Manager | Illustrative Data
Example Data | EX-PIP-032 | 4 - Implement | Supplier Controls | Evaluate priority suppliers/processors and close onboarding/contract gaps. | Supplier privacy evidence | Procurement Privacy Lead | Medium | EX-PIP-020 | 2026-10-01 | 2026-10-31 | 25% | Blocked |  |  | Two supplier reviews depend on updated processing scope | Project Manager | Illustrative Data
Example Data | EX-PIP-036 | 5 - Validate | Internal Audit | Conduct internal PIMS audit using objective evidence. | Internal privacy audit report | Lead Privacy Auditor | Low | EX-PIP-032 | 2026-11-16 | 2026-11-27 | 0% | Not Started |  |  | Dependent on sufficient operating evidence | Project Manager | Illustrative Data
| PIP-001 | 1 - Initiate | Governance | Confirm executive sponsor and PIMS implementation governance. | Approved project governance / steering structure | Executive Sponsor | High |  |  |  | 0%
| PIP-002 | 1 - Initiate | Objectives | Confirm implementation objectives, success criteria and intended outcomes. | Project charter / objectives | Project Manager | High | PIP-001 |  |  | 0%
| PIP-003 | 1 - Initiate | Scope | Define preliminary organizational, processing, system and location scope. | Approved implementation scope | Privacy Lead | High | PIP-001 |  |  | 0%
| PIP-004 | 1 - Initiate | Stakeholders | Identify privacy, legal, security, data, procurement, HR, technology and business stakeholders. | Stakeholder map | Project Manager | Medium | PIP-003 |  |  | 0%
| PIP-005 | 1 - Initiate | Plan | Baseline detailed schedule, resources, communications and project risks. | Approved implementation project plan | Project Manager | High | PIP-001,PIP-003 |  |  | 0%
| PIP-006 | 2 - Assess | Gap Analysis | Complete ISO/IEC 27701 privacy gap analysis. | Gap analysis | Lead Assessor | High | PIP-003 |  |  | 0%
| PIP-007 | 2 - Assess | Processing Inventory | Establish or validate material PII processing inventory. | Processing inventory | Privacy Operations Lead | High | PIP-003 |  |  | 0%
| PIP-008 | 2 - Assess | Data Flows | Map material PII flows, systems, recipients, locations and deletion paths. | PII data-flow maps | Data Governance Lead | High | PIP-007 |  |  | 0%
| PIP-009 | 2 - Assess | Privacy Roles | Identify controller, processor and other relevant roles for material processing. | Role assessment | Privacy Lead | High | PIP-007 |  |  | 0%
| PIP-010 | 2 - Assess | Requirements | Identify applicable privacy obligations, contracts and stakeholder requirements from authoritative sources. | Privacy requirements register | Legal / Privacy Counsel | High | PIP-007 |  |  | 0%
| PIP-011 | 2 - Assess | Risk Method | Review current privacy risk and impact assessment methods. | Method assessment | Privacy Risk Lead | High | PIP-006 |  |  | 0%
| PIP-012 | 2 - Assess | PII Requests | Assess privacy-request intake, identity verification, routing and response processes. | Request process assessment | Privacy Operations Lead | Medium | PIP-006 |  |  | 0%
| PIP-013 | 2 - Assess | Suppliers | Assess supplier/processor due diligence, contracts, sub-processors and monitoring. | Supplier privacy assessment | Procurement Privacy Lead | High | PIP-006 |  |  | 0%
| PIP-014 | 2 - Assess | Retention / Transfers | Assess retention, deletion, processing locations and transfer governance. | Lifecycle / transfer assessment | Data Governance Lead | High | PIP-006 |  |  | 0%
| PIP-015 | 2 - Assess | Incidents | Assess privacy-incident detection, escalation, investigation and notification support. | Incident process assessment | Privacy Incident Lead | High | PIP-006 |  |  | 0%
| PIP-016 | 2 - Assess | Action Planning | Prioritize validated gaps and approve implementation action plan. | Approved privacy action plan | PIMS Steering Group | High | PIP-006 |  |  | 0%
| PIP-017 | 3 - Design | PIMS Framework | Design PIMS governance, process framework and interfaces. | PIMS framework | Privacy Lead | High | PIP-016 |  |  | 0%
| PIP-018 | 3 - Design | Policy / Objectives | Develop privacy policy, objectives and indicators framework. | Policy/objectives package | Privacy Lead | Medium | PIP-017 |  |  | 0%
| PIP-019 | 3 - Design | Documented Information | Define privacy document/record controls and repository structure. | Documented information design | Document Controller | Medium | PIP-017 |  |  | 0%
| PIP-020 | 3 - Design | Privacy Risk | Define approved privacy risk and impact assessment method. | Privacy risk / impact method | Privacy Risk Lead | High | PIP-011,PIP-017 |  |  | 0%
| PIP-021 | 3 - Design | Privacy by Design | Define project/change privacy review and escalation criteria. | Privacy-by-design workflow | Privacy Risk Lead | High | PIP-017 |  |  | 0%
| PIP-022 | 3 - Design | PII Requests | Design request intake, verification/routing, ownership and evidence requirements. | PII principal request procedure | Privacy Operations Lead | High | PIP-012,PIP-017 |  |  | 0%
| PIP-023 | 3 - Design | Supplier Privacy | Define supplier/processor evaluation, contracting, sub-processor and monitoring controls. | Supplier privacy framework | Procurement Privacy Lead | High | PIP-013,PIP-017 |  |  | 0%
| PIP-024 | 3 - Design | Retention / Deletion | Define retention, deletion/return and evidence controls for material PII. | Retention/deletion framework | Data Governance Lead | High | PIP-014,PIP-017 |  |  | 0%
| PIP-025 | 3 - Design | Transfers / Locations | Define location register and applicable transfer-governance controls. | Location/transfer framework | Privacy Lead | High | PIP-014,PIP-017 |  |  | 0%
| PIP-026 | 3 - Design | Incidents | Define privacy-incident roles, decision inputs, evidence and notification support. | Privacy incident procedure | Privacy Incident Lead | High | PIP-015,PIP-017 |  |  | 0%
| PIP-027 | 3 - Design | Monitoring | Define PIMS KPIs, audit, management review and improvement controls. | PIMS performance framework | Privacy Lead | Medium | PIP-017 |  |  | 0%
| PIP-028 | 4 - Implement | Document Deployment | Approve and issue controlled PIMS procedures, guidance, templates and registers. | Controlled PIMS document set | Document Controller | High | PIP-018:PIP-027 |  |  | 0%
| PIP-029 | 4 - Implement | Training / Awareness | Deliver role-based privacy training and awareness. | Training / awareness evidence | Privacy Training Lead | High | PIP-028 |  |  | 0%
| PIP-030 | 4 - Implement | Processing Inventory | Populate and validate processing inventory and material data flows. | Validated processing inventory | Privacy Operations Lead | High | PIP-007,PIP-008,PIP-028 |  |  | 0%
| PIP-031 | 4 - Implement | Risk Assessments | Perform prioritized privacy risk/impact assessments and treatments. | Risk/impact records | Privacy Risk Lead | High | PIP-020,PIP-028 |  |  | 0%
| PIP-032 | 4 - Implement | Supplier Controls | Evaluate priority suppliers/processors and close onboarding/contract gaps. | Supplier privacy evidence | Procurement Privacy Lead | High | PIP-023,PIP-028 |  |  | 0%
| PIP-033 | 4 - Implement | Request Operations | Implement and test PII-principal request workflow. | Request handling evidence | Privacy Operations Lead | High | PIP-022,PIP-029 |  |  | 0%
| PIP-034 | 4 - Implement | Lifecycle Controls | Implement retention/deletion and location/transfer registers and priority controls. | Lifecycle/transfer evidence | Data Governance Lead | High | PIP-024,PIP-025 |  |  | 0%
| PIP-035 | 4 - Implement | Incident Readiness | Implement/test privacy-incident workflow and decision support. | Exercise / incident-readiness evidence | Privacy Incident Lead | High | PIP-026,PIP-029 |  |  | 0%
| PIP-036 | 5 - Validate | Internal Audit | Conduct internal PIMS audit using objective evidence. | Internal privacy audit report | Lead Privacy Auditor | High | PIP-028:PIP-035 |  |  | 0%
| PIP-037 | 5 - Validate | Performance Review | Review initial PIMS indicators, risks, requests, incidents and supplier results. | PIMS validation report | Privacy Lead | High | PIP-030:PIP-036 |  |  | 0%
| PIP-038 | 5 - Validate | Corrective Action | Close high-priority validation/audit findings with effectiveness evidence. | Corrective action evidence | Project Manager | High | PIP-036,PIP-037 |  |  | 0%
| PIP-039 | 5 - Validate | Management Review | Conduct implementation management review and approve operational readiness. | Management review minutes | Executive Sponsor | High | PIP-038 |  |  | 0%
| PIP-040 | 6 - Handover & Improve | Handover | Transfer PIMS ownership, calendars, dashboards, actions and repositories to operational owners. | Operational handover pack | Project Manager | High | PIP-039 |  |  | 0%
| PIP-041 | 6 - Handover & Improve | Improvement Plan | Establish post-implementation improvement backlog and review cadence. | PIMS improvement plan | Privacy Lead | Medium | PIP-039 |  |  | 0%
| PIP-042 | 6 - Handover & Improve | Project Closure | Complete lessons learned, closure report and sponsor sign-off. | Project closure report | Project Manager | Medium | PIP-040,PIP-041 |  |  | 0%
Formulas:
Schedule Flag = IF([Data Type]<>"Actual Data","",IF(OR([Status]="Completed",[Status]="N/A"),[Status],IF([Planned Finish]="","",IF([Planned Finish]<TODAY(),"Overdue",IF([Planned Finish]-TODAY()<=7,"Due Soon","On Track")))))

## Dashboard
Privacy Implementation Dashboard
Document Code: PIMS-PLN-001 ¦ Version: 1.0 ¦ Effective Date: 2026-09-18 ¦ Applied Standard: ISO/IEC 27701:2025 ¦ Classification: INTERNAL
Copyright © ISO Toolkits ¦ www.iso-toolkits.org ¦ info@iso-toolkits.org
[Note] Example Data is used only to demonstrate charts while no Actual Data exists. KPI/Summary always excludes Example Data.
Chart Data Mode | Illustrative Data
Actual KPI | Result
Actual Tasks | 0
Completed | 0
In Progress | 0
Blocked | 0
Not Started | 0
Overdue | 0
High Priority Open | 0
Average % Complete | 0%
Actual Completion % | 0%
Example Rows (excluded) | 5

## Chart Data
Chart Data - Privacy Project Plan
Document Code: PIMS-PLN-001 ¦ Version: 1.0 ¦ Effective Date: 2026-09-18 ¦ Applied Standard: ISO/IEC 27701:2025 ¦ Classification: INTERNAL
Copyright © ISO Toolkits ¦ www.iso-toolkits.org ¦ info@iso-toolkits.org
Chart Data Mode | Value
Mode | Illustrative Data
Status | Count | Phase | Count
Not Started | 1 | 1 - Initiate | 1
In Progress | 1 | 2 - Assess | 1
Blocked | 1 | 3 - Design | 1
Completed | 2 | 4 - Implement | 1
N/A | 0 | 5 - Validate | 1
|  | 6 - Handover & Improve | 0

## Reference Data
Reference Data
Document Code: PIMS-PLN-001 ¦ Version: 1.0 ¦ Effective Date: 2026-09-18 ¦ Applied Standard: ISO/IEC 27701:2025 ¦ Classification: INTERNAL
Copyright © ISO Toolkits ¦ www.iso-toolkits.org ¦ info@iso-toolkits.org
List | Value | Description | Source / Note
Data Type | Example Data | Illustrative row; excluded from Actual KPI/Summary.
Data Type | Actual Data | Operational row; included in Actual KPI/Summary.
Priority | High
Priority | Medium
Priority | Low
Standard | ISO/IEC 27701:2025 | Privacy information management systems — Requirements and guidance. | https://www.iso.org/standard/27701
Privacy Role | PII Controller | Use only where supported by actual processing/accountability context.
Privacy Role | PII Processor | Use only where supported by actual processing/accountability context.
Phase | 1 - Initiate
Phase | 2 - Assess
Phase | 3 - Design
Phase | 4 - Implement
Phase | 5 - Validate
Phase | 6 - Handover & Improve
Status | Not Started
Status | In Progress
Status | Blocked
Status | Completed
Status | N/A
[Note] Applicable privacy laws, regulatory obligations, contractual terms, data-residency or transfer requirements must be verified for the relevant jurisdictions and processing context before controlled use.

## Revision History
Revision History
Document Code: PIMS-PLN-001 ¦ Version: 1.0 ¦ Effective Date: 2026-09-18 ¦ Applied Standard: ISO/IEC 27701:2025 ¦ Classification: INTERNAL
Copyright © ISO Toolkits ¦ www.iso-toolkits.org ¦ info@iso-toolkits.org
Version | Date | Description
1.0 | 2026-09-18 | Initial issue