## Instructions
Energy Management Implementation Project Plan
Enterprise-ready ISO 50001 implementation project planner with a task library, working project plan, schedule controls and an Actual-vs-Illustrative dashboard.
How to use
1 | Review Task Library and select the tasks applicable to the organization's EnMS scope and implementation strategy.
2 | Use Project Plan for the live implementation schedule; assign owner roles, dates, dependencies and status.
3 | The first five rows in Project Plan are Example Data and may be deleted once Actual Data is entered.
4 | Dashboard KPIs count Actual Data only; the status chart switches automatically from Example Data to Actual Data.
5 | Review the plan at each project governance meeting and escalate blocked high-priority tasks.
[Note] Example Data / Illustrative Data is provided only to demonstrate use. Replace or delete it before the workbook becomes a controlled organizational record.
References
ISO 50001:2018 — Energy management systems — Requirements with guidance for use | https://www.iso.org/standard/69426.html
ISO 50001:2018/Amd 1:2024 — Climate action changes | https://www.iso.org/standard/88430.html
ISO 50004:2020 — Guidance for implementation, maintenance and improvement of an ISO 50001 EnMS | https://www.iso.org/standard/74863.html
ISO 50005:2021 — Guidelines for a phased implementation | https://www.iso.org/standard/76428.html
ISO 50006:2023 — Evaluating energy performance using EnPIs and energy baselines | https://www.iso.org/standard/79367.html

## Reference Data
Reference Data & Controlled Lists
Data Type | Priority | Status | Assessment Status | Document Status | Action Need | Yes / No / N/A | Phase
Example Data | High | Not Started | Not Assessed | Not Drafted | No Action | Yes | Initiation
Actual Data | Medium | Planned | Fully Implemented | Draft | Improve | No | Context & Scope
| Low | Open | Partially Implemented | Under Review | Correct | N/A | Leadership
|  | In Progress | Not Implemented | Approved | Create / Implement |  | Planning
|  | Blocked | N/A | Implemented | Verify |  | Support
|  | Completed |  | Obsolete |  |  | Operation
|  | Closed |  | N/A |  |  | Performance Evaluation
Improvement
Certification Readiness
Official ISO references used in this toolkit
ISO 50001:2018 — Energy management systems — Requirements with guidance for use | https://www.iso.org/standard/69426.html
ISO 50001:2018/Amd 1:2024 — Climate action changes | https://www.iso.org/standard/88430.html
ISO 50004:2020 — Guidance for implementation, maintenance and improvement of an ISO 50001 EnMS | https://www.iso.org/standard/74863.html
ISO 50005:2021 — Guidelines for a phased implementation | https://www.iso.org/standard/76428.html
ISO 50006:2023 — Evaluating energy performance using EnPIs and energy baselines | https://www.iso.org/standard/79367.html

## Task Library
ISO 50001 Implementation Task Library
Document Code | EnMS-PLN-001-LIB | Version | 1.0 | Classification | INTERNAL
Applicable Standard | ISO 50001:2018 + Amendment 1:2024 | Effective Date | 2026-09-19 | Document Owner | [DOCUMENT OWNER]
Website | www.iso-toolkits.org | Email | info@iso-toolkits.org | Organization | [ORGANIZATION NAME]
[Note] Task Library rows are reusable implementation content, not organizational progress data. Copy only applicable tasks into Project Plan.
Library ID | Phase | Implementation Activity | Purpose / Outcome | Key Deliverable | Typical Owner Role | Dependency / Input | Recommended Evidence | Applicable? | Notes
TL-001 | Initiation | Appoint executive sponsor and Energy Manager | Establish visible leadership and project accountability. | Appointment / project authorization | Top Management |  | Approved appointment / project charter
TL-002 | Initiation | Form cross-functional energy team | Bring operational, engineering, finance, procurement and support functions into implementation. | Energy team roster | Energy Manager | TL-001 | Team appointment and meeting cadence
TL-003 | Initiation | Approve implementation charter, scope and governance | Define project objectives, reporting, milestones and decision rights. | Project charter | Executive Sponsor / Energy Manager | TL-001 | Approved charter
TL-004 | Initiation | Establish implementation document repository | Create controlled workspace for project and EnMS documented information. | Controlled repository | Document Controller | TL-003 | Folder structure / access controls
TL-005 | Context & Scope | Review organizational context including climate-related issues where relevant | Identify issues that can affect intended EnMS outcomes. | Context review | Energy Manager | TL-003 | Context and issue register
TL-006 | Context & Scope | Identify interested parties and relevant energy requirements | Capture needs and requirements relevant to energy performance and EnMS. | Interested-party requirements register | Energy Manager / Legal | TL-005 | Requirement register
TL-007 | Context & Scope | Define EnMS scope and boundaries | Set organizational and physical coverage for the EnMS. | Approved EnMS scope & boundaries | Top Management / Energy Manager | TL-005, TL-006 | Controlled scope statement
TL-008 | Leadership | Draft and approve energy policy | Establish commitments and strategic direction for energy management. | Approved energy policy | Top Management | TL-007 | Signed/approved policy
TL-009 | Leadership | Assign EnMS roles, responsibilities and authorities | Clarify ownership of energy review, SEUs, EnPIs, audit and improvement. | Responsibility matrix / appointments | Top Management / Energy Manager | TL-007 | RACI / role records
TL-010 | Planning | Identify EnMS risks and opportunities | Plan actions that support intended outcomes and improvement. | Risk & opportunity register | Energy Manager / Energy Team | TL-005, TL-006 | Approved register and actions
TL-011 | Planning | Collect historical energy data | Build the data foundation for the energy review and baselines. | Validated energy data pack | Energy Analyst | TL-007 | Utility bills, meter exports, fuel data
TL-012 | Planning | Map energy sources and major energy uses | Establish where and how energy is consumed across the scope. | Energy flow / use map | Energy Team | TL-011 | Energy balance / process map
TL-013 | Planning | Conduct the energy review | Analyze energy use, consumption and performance. | Energy review | Energy Team | TL-011, TL-012 | Approved review record
TL-014 | Planning | Identify significant energy uses | Prioritize material energy uses using defined criteria. | SEU register | Energy Manager / Operations | TL-013 | SEU criteria and ranking
TL-015 | Planning | Identify relevant variables and static factors | Support fair energy-performance evaluation and normalization. | Variable/static factor register | Energy Analyst | TL-013, TL-014 | Analysis and rationale
TL-016 | Planning | Define EnPIs | Select indicators that measure energy performance for the organization and SEUs. | EnPI register | Energy Analyst | TL-014, TL-015 | Calculation method / ownership
TL-017 | Planning | Establish energy baselines | Create representative baseline references for EnPIs. | Energy baseline register | Energy Analyst | TL-016 | Baseline method and approval
TL-018 | Planning | Create energy data collection plan | Define meters, data sources, collection frequency and data-quality controls. | Energy data collection plan | Energy Manager / Metering Owner | TL-016, TL-017 | Meter/data plan
TL-019 | Planning | Set energy objectives, targets and action plans | Translate energy review priorities into measurable implementation and improvement actions. | Objectives, targets & action plans | Top Management / Energy Manager | TL-013, TL-016, TL-017 | Approved objectives and action plans
TL-020 | Support | Perform competence and training needs analysis | Ensure roles affecting energy performance are competent. | Training / competence plan | HR / Energy Manager | TL-009, TL-014 | Competence matrix
TL-021 | Support | Deliver awareness and role-based training | Build practical understanding of SEUs, controls and EnMS responsibilities. | Training records | HR / Energy Manager | TL-020 | Attendance / competence evidence
TL-022 | Support | Establish communication arrangements | Define internal and external communication for the EnMS. | Communication plan | EnMS Coordinator | TL-009 | Approved communication plan
TL-023 | Support | Establish documented information controls | Ensure documents and records are controlled, available and protected. | Document control process | Document Controller | TL-004 | Procedure and master register
TL-024 | Operation | Define operational controls for SEUs | Control operating parameters that materially affect energy performance. | SEU operating controls | Operations / Maintenance | TL-014, TL-016 | Procedures, setpoints, logs
TL-025 | Operation | Align preventive maintenance with SEU performance | Integrate energy performance considerations into maintenance practices. | SEU maintenance controls | Maintenance Manager | TL-014 | PM tasks and records
TL-026 | Operation | Integrate energy performance into design | Consider improvement opportunities in relevant design and modification activities. | Design review process | Engineering Manager | TL-019 | Design review records
TL-027 | Operation | Integrate energy performance into procurement | Define energy-related procurement specifications and evaluation criteria. | Procurement criteria | Procurement Manager | TL-019 | Tender/specification criteria
TL-028 | Performance Evaluation | Implement monitoring, measurement and analysis | Generate reliable information for EnPI, baseline and objective review. | Monitoring & analysis routine | Energy Analyst | TL-018 | Dashboards / trend reports
TL-029 | Performance Evaluation | Verify metering and data quality | Maintain confidence in energy data used for decisions. | Meter verification / calibration evidence | Utilities / Maintenance | TL-018 | Meter register / verification records
TL-030 | Performance Evaluation | Establish internal audit programme | Plan audit coverage, timing and competence. | Internal audit programme | Lead Internal Auditor | TL-023, TL-024 | Approved audit programme
TL-031 | Performance Evaluation | Conduct internal EnMS audit | Confirm implementation and identify evidence-based findings. | Audit report & actions | Lead Internal Auditor | TL-030 | Audit records
TL-032 | Performance Evaluation | Conduct management review | Evaluate EnMS performance and make strategic decisions. | Management review minutes & actions | Top Management / Energy Manager | TL-028, TL-031 | Approved minutes/actions
TL-033 | Improvement | Close nonconformities and corrective actions | Correct identified issues and verify effectiveness. | Closed CAPA records | Process Owners / EnMS Coordinator | TL-031 | Corrective action evidence
TL-034 | Improvement | Verify energy performance improvements | Confirm actual improvement against baselines/EnPIs. | Verified savings / performance report | Energy Analyst / Finance | TL-028, TL-019 | Measurement/analysis evidence
TL-035 | Certification Readiness | Complete final readiness review | Check system maturity, open gaps and objective evidence before certification. | Readiness review report | Energy Manager / Lead Auditor | TL-031, TL-032, TL-033 | Readiness checklist
TL-036 | Certification Readiness | Close pre-certification actions | Resolve critical gaps and organize certification evidence. | Closed readiness action plan | Process Owners | TL-035 | Closure evidence

## Project Plan
Energy Management Implementation Project Plan
Document Code | EnMS-PLN-001 | Version | 1.0 | Classification | INTERNAL
Applicable Standard | ISO 50001:2018 + Amendment 1:2024 | Effective Date | 2026-09-19 | Document Owner | [DOCUMENT OWNER]
Website | www.iso-toolkits.org | Email | info@iso-toolkits.org | Organization | [ORGANIZATION NAME]
[Note] The first five rows are Example Data only. Use Data Type = Actual Data for the live implementation plan; dashboard KPIs exclude Example Data.
Task ID | Phase | Activity | Key Deliverable | Owner Role | Priority | Planned Start | Due Date | Duration (days) | Dependency | Status | % Complete | Evidence / Link | Risk / Issue | Next Step | Data Type
EX-PRJ-001 | Initiation | Appoint executive sponsor and Energy Manager | Approved appointments | Top Management | High | 2026-09-21 | 2026-09-25 | 5 |  | Completed | 100% | Signed appointment memo |  | Launch project charter | Example Data
EX-PRJ-002 | Context & Scope | Define EnMS scope and boundaries | Approved scope statement | Energy Manager | High | 2026-09-28 | 2026-10-07 | 10 | EX-PRJ-001 | In Progress | 55% | Draft scope v0.2 | Remote warehouse boundary needs confirmation | Confirm site boundary | Example Data
EX-PRJ-003 | Planning | Collect historical energy data | Validated 24-month data pack | Energy Analyst | High | 2026-10-01 | 2026-10-20 | 20 | EX-PRJ-001 | Open | 30% | Electricity and gas data received | Missing sub-meter export for Line 4 | Recover missing data | Example Data
EX-PRJ-004 | Support | Establish documented information controls | EnMS document control process | Document Controller | Medium | 2026-10-05 | 2026-10-16 | 12 | EX-PRJ-001 | Blocked | 15% | Existing IMS document procedure | Repository permissions pending | Confirm controlled workspace | Example Data
EX-PRJ-005 | Performance Evaluation | Plan internal audit programme | Approved audit programme | Lead Internal Auditor | Medium | 2026-11-09 | 2026-11-20 | 12 | EX-PRJ-002 | Planned | 0% |  | Depends on core EnMS implementation | Draft audit scope | Example Data

## Dashboard
EnMS Implementation Project Dashboard
Document Code | EnMS-RPT-011 | Version | 1.0 | Classification | INTERNAL
Applicable Standard | ISO 50001:2018 + Amendment 1:2024 | Effective Date | 2026-09-19 | Document Owner | [DOCUMENT OWNER]
Website | www.iso-toolkits.org | Email | info@iso-toolkits.org | Organization | [ORGANIZATION NAME]
[Note] KPI cards show Actual Data only. Status chart uses Illustrative Data until at least one Actual Data task is entered.
KPI | Value |  | Chart Control | Value
Actual Tasks | 0 |  | Chart Data Mode | Illustrative Data
Completed / Closed | 0 |  | Chart Source Type | Example Data
In Progress | 0
Blocked | 0
High Priority Open | 0 |  | Status | Count
Average % Complete | 0% |  | Not Started | 0
Overdue Open Tasks | 0 |  | Planned | 1
|  |  | In Progress | 1
|  |  | Blocked | 1
|  |  | Completed | 1