Laboratory Quality Implementation Project Plan

Practical implementation roadmap for ISO 15189:2022

ISO 15189:2022 — Medical laboratories — Requirements for quality and competence

| Document Code | LQMS-PLN-001 | Version | 1.0 |
| --- | --- | --- | --- |
| Effective Date | 2026-09-19 | Classification | INTERNAL |
| Document Owner | [DOCUMENT OWNER] | Approver | [APPROVER] |
| Organization | [ORGANIZATION NAME] | Review Cycle | [ANNUAL / UPON CHANGE] |
| Website | www.iso-toolkits.org | Email | info@iso-toolkits.org |

[Note] Replace organization-specific placeholders and confirm applicable statutory, regulatory, accreditation and payer requirements before controlled release.

# 1. Project Purpose

This plan provides a practical implementation roadmap for establishing, upgrading or aligning a medical laboratory quality management system with ISO 15189:2022. It is designed for use by the laboratory director, quality manager, technical managers, section heads and project stakeholders to coordinate work, evidence, decisions and readiness milestones.

# 2. Project Objectives

Establish a documented LQMS that is integrated with routine laboratory operations rather than managed as a separate compliance project.

Demonstrate technical competence across personnel, equipment, examination procedures, quality control and result reporting.

Strengthen patient safety through risk-based controls, reliable communication and effective response to nonconforming work.

Create objective evidence sufficient for internal assurance, management review and accreditation-readiness assessment.

Transfer ownership from the implementation project to routine process owners before project closure.

# 3. Governance and Roles

| Role | Accountability | Typical responsibilities |
| --- | --- | --- |
| Executive Sponsor / Laboratory Director | Accountable for project success and laboratory competence. | Approve scope, policy, resources, major decisions and readiness status. |
| Quality Manager / Project Lead | Coordinates LQMS implementation. | Maintain plan, facilitate gap closure, control documents, track evidence and report progress. |
| Technical Manager(s) | Accountable for technical competence. | Method verification/validation, QC/EQA, equipment, technical authorization and performance monitoring. |
| Section Heads / Process Owners | Own implementation in daily work. | Develop SOPs, train staff, maintain records, close actions and sustain controls. |
| IT / Facilities / Procurement / HR | Provide enabling controls. | Information systems, environment, provider control, personnel records and support services. |
| Internal Audit Lead | Provides independent assurance. | Plan and conduct audit, report findings, verify corrective actions. |

# 4. Illustrative Implementation Roadmap

[Note] The schedule below is Illustrative Data. Adjust duration, sequence and resources to the laboratory’s size, complexity, maturity, accreditation body requirements and operational constraints.

| Phase | Illustrative timing | Primary focus | Exit criteria |
| --- | --- | --- | --- |
| 0. Mobilize | Weeks 1–2 | Sponsor, project governance, scope, repository, implementation team. | Project charter and responsibilities approved. |
| 1. Diagnose | Weeks 2–4 | Gap analysis, document review, process interviews, evidence sampling. | Prioritized gap register and action plan approved. |
| 2. Design LQMS | Weeks 4–7 | Manual, policy, document hierarchy, risk model, objectives and governance controls. | Core LQMS framework approved. |
| 3. Resource competence | Weeks 6–10 | Personnel competence, facilities, equipment, reagents, suppliers and information systems. | Resource controls implemented with evidence. |
| 4. Technical processes | Weeks 8–14 | Pre-examination, examination, post-examination, method verification/validation, QC/EQA. | Technical procedures controlled and staff trained. |
| 5. Operate & evidence | Weeks 12–17 | Run controls, collect records, monitor indicators, close implementation issues. | Sufficient routine evidence available. |
| 6. Internal assurance | Weeks 16–19 | Internal audit, nonconformity correction, management review. | Major gaps closed; management decisions recorded. |
| 7. Readiness & handover | Weeks 19–20+ | Readiness review, evidence indexing, ownership transfer, accreditation preparation. | Controlled handover and readiness decision. |

# 5. Detailed Work Plan

| ID | Phase | Activity | Owner | Deliverable / Evidence | Dependency | Priority | Illustrative Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| P-001 | Mobilize | Appoint sponsor, project lead and cross-functional implementation team. | Laboratory Director | Approved appointments and governance terms | — | High | Example: Completed |
| P-002 | Mobilize | Define project scope, laboratory sites, disciplines and POCT interfaces. | Project Lead | Approved project scope | P-001 | High | Example: In Progress |
| P-003 | Mobilize | Establish controlled implementation repository and document conventions. | Quality Manager | Repository and naming/control rules | P-001 | Medium | Example: Completed |
| P-004 | Diagnose | Perform structured ISO 15189 gap analysis. | Quality Manager / Assessors | Gap analysis report | P-002 | High | Example: In Progress |
| P-005 | Diagnose | Create prioritized gap-closure action plan. | Project Lead / Process Owners | Approved action plan | P-004 | High | Example: Planned |
| P-006 | Design LQMS | Approve LQMS scope and service profile. | Laboratory Director | Controlled scope statement | P-002 | High | Example: Planned |
| P-007 | Design LQMS | Develop or update quality policy and objectives. | Laboratory Director / Quality Manager | Approved policy and objective register | P-004 | High | Example: Planned |
| P-008 | Design LQMS | Define LQMS document architecture and master document register. | Quality Manager | Document map and register | P-003 | Medium | Example: Planned |
| P-009 | Design LQMS | Implement risk and opportunity management process. | Quality Manager | Risk procedure and risk register | P-004 | High | Example: Planned |
| P-010 | Resources | Confirm role descriptions, qualification criteria and authorizations. | Laboratory Director / HR | Role and authorization matrix | P-006 | High | Example: Planned |
| P-011 | Resources | Establish competence assessment and continuing education controls. | Section Heads / HR | Competence matrix and assessment plan | P-010 | High | Example: Planned |
| P-012 | Resources | Review facilities and environmental controls. | Facilities / Section Heads | Environmental control plan and records | P-004 | Medium | Example: Planned |
| P-013 | Resources | Review equipment lifecycle, maintenance and metrological controls. | Technical Manager | Equipment procedure/register/files | P-004 | High | Example: Planned |
| P-014 | Resources | Review reagent, consumable and inventory controls. | Section Heads | Reagent control process and records | P-004 | High | Example: Planned |
| P-015 | Resources | Evaluate external providers and referral laboratory controls. | Procurement / Laboratory Director | Approved provider controls | P-004 | Medium | Example: Planned |
| P-016 | Information | Validate LIS/data flows, access, interfaces, backup and downtime arrangements. | IT / Laboratory Director | LIS validation and continuity evidence | P-004 | High | Example: Planned |
| P-017 | Pre-examination | Control examination requests, patient identification and sample collection. | Pre-examination Lead | Controlled procedures and training records | P-010 | High | Example: Planned |
| P-018 | Pre-examination | Control sample transport, receipt, acceptance and rejection. | Specimen Reception Lead | Procedures, criteria and exception records | P-017 | High | Example: Planned |
| P-019 | Examination | Inventory methods and confirm verification/validation status. | Technical Manager | Method inventory and technical files | P-013 | High | Example: Planned |
| P-020 | Examination | Standardize examination SOP structure and technical authorization. | Section Heads | Approved SOP set | P-019 | High | Example: Planned |
| P-021 | Examination | Implement IQC review and response-to-failure controls. | Section Heads | IQC procedure and review records | P-020 | High | Example: Planned |
| P-022 | Examination | Implement EQA/PT evaluation and investigation controls. | Quality Manager / Section Heads | EQA/PT procedure and investigations | P-020 | High | Example: Planned |
| P-023 | Post-examination | Control result review, authorization, report release and amendments. | Technical Manager | Reporting procedures and authorization matrix | P-020 | High | Example: Planned |
| P-024 | Post-examination | Control critical-result communication and escalation. | Section Heads | Critical-result procedure and records | P-023 | High | Example: Planned |
| P-025 | Quality | Implement nonconforming work, complaint and CAPA processes. | Quality Manager | Procedures and registers | P-008 | High | Example: Planned |
| P-026 | Quality | Launch quality indicators and trend review. | Quality Manager / Process Owners | Indicator definitions and dashboard | P-007 | Medium | Example: Planned |
| P-027 | Evidence | Run the LQMS and accumulate representative records. | All Process Owners | Routine operational evidence | P-017–P-026 | High | Example: Planned |
| P-028 | Assurance | Conduct internal audit across management and technical processes. | Internal Audit Lead | Audit report and findings | P-027 | High | Example: Planned |
| P-029 | Assurance | Close significant audit findings and verify effectiveness. | Process Owners / Quality Manager | Closed CAPA records | P-028 | High | Example: Planned |
| P-030 | Assurance | Conduct formal management review. | Laboratory Director | Approved minutes and actions | P-028 | High | Example: Planned |
| P-031 | Readiness | Perform final readiness assessment and evidence-index review. | Project Lead / Independent Reviewer | Readiness report | P-029,P-030 | High | Example: Planned |
| P-032 | Handover | Transfer open actions, document ownership and governance cadence to routine operations. | Project Lead / Process Owners | Handover record | P-031 | Medium | Example: Planned |

# 6. Project Controls

Weekly implementation review: progress, blockers, decisions, overdue evidence and next-week priorities.

Monthly sponsor review: major risks, resourcing, cross-functional barriers and readiness trajectory.

Controlled change: significant changes to scope, methods, equipment, LIS or service model should be evaluated for project and LQMS impact.

Evidence acceptance: a task is not complete until the required controlled document, record, training or verification evidence exists.

Escalation: patient-safety risks, serious competence gaps or inability to assure result reliability should be escalated immediately rather than deferred to routine project governance.

# 7. Project Completion and Handover

| Completion criterion | Expected evidence |
| --- | --- |
| Governance embedded | Approved scope, policy, roles and routine governance calendar. |
| Technical controls operational | Approved procedures, competent authorized staff and representative technical records. |
| Performance controls active | Indicators, QC/EQA review, nonconformity/CAPA, complaint and risk records. |
| Assurance completed | Internal audit and management review completed with significant actions controlled. |
| Ownership transferred | Named owners, review frequencies and outstanding actions accepted into business-as-usual governance. |

# References

| Reference | Title | Official source |
| --- | --- | --- |
| ISO 15189:2022 | Medical laboratories — Requirements for quality and competence | https://www.iso.org/standard/76677.html |
| ISO 20658:2023 | Requirements for the collection and transport of samples for medical laboratory examinations | https://www.iso.org/standard/80035.html |
| ISO 22367:2026 | Medical laboratories — Application of risk management to medical laboratories | https://www.iso.org/standard/87738.html |

[Note] Use the organization’s authorized copy of the applicable standard as the definitive reference. This document paraphrases requirements and does not reproduce the standard text.

# Revision and Approval

| Version | Date | Description | Approval Status |
| --- | --- | --- | --- |
| 1.0 | 2026-09-19 | Initial issue | Approved / [STATUS] |
| Prepared by | Reviewed by | Approved by | Approval Date |
| [DOCUMENT OWNER] | [REVIEWER] | [APPROVER] | [DATE] |